## Sheet1
Task | Comment | Estimate (Days) | Priority
Cut, copy and paste sequences | Partially implemented | 5 | 10
Timeline: Scrolling back | Timeline does not remember what is supposed to be on(Stateless) | 14 | 10
Resizeable simulator | Allow the simulator to be drawn at all sizes | 14 | 12
Fade up and fade down | Slowly dim lights up and down (dimmer switch) | 7 | 15
Control intensity of light (currently on or off at 100%) | Control how bright the light is (wattage) | 7 | 15
Transperancy of the water. Front curtain. Rings. | Reorder what is shown in front or transparent | 2 | 18
Zipping files together | Create one file for easy | 2 | 20
Add Channels - doesn't add properly | Update arraylists properly, ensure they behave as expected | 14 | 20
Advanced Feature | Show more controls/redo GUI | 20 | 25
Beat lines | points on timeline that the choreographer can flag | 5 | 25
JavaFX on simulator | Make it look more realistic | 14 | 26
Add labels to items | Identify what is being shown on the screen | 1 | 30
Add Tooltips | Tooltips | 1 | 30
Make user guide | Update user manual | 10 | 30
Waveform Graph | Visualization of music file | 14 | 30
Password protect advanced feature | Add password to advanced feature section | 2 | 45
Add support for different music files | Open wav, flac, mp3... | 14 | 100